## Sheet1
Team 3.14, the RaspberryPi Temperature/Humidity Project
Marcel Englmaier, Jason Pearson, Mike Guzior, Justin Koehler
| Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
| Research Chipset to use | 1:00 | 2 | 1:00 | 1 | Marcel
| Research Temperature Sensor | 1:00 | 2 | 5:00 | 1 | Marcel
| Research Humidity Sensor | 1:00 | 2 | 1:25 | 1 | Marcel
| Acquire Specs from Client(Dr. Kapenga) | 1:00 | 10 | 1:00 | 1 | All
| Set up Git repo | 5:00 | 1 | 1:00 | 1 | Marcel
| Aquire old source code from Andrew | 2:00 | 6 | 2:00 | 1 | All
| Feasability Report-First Draft | 7:00 | 3 | 5:00 | 1 | All
| Install and configure Raspbian on one RaspberryPi | 2:00 | 3 | 1:00 | 1 | Marcel
| Install Laravel web server onto CS machines | 3:00 | 5 | 4:00 | 1 | Justin
| Organize repo into correct subfolders | 1:00 | 10 | 1:00 | 1 | All
# | Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
1 | Feasability Report-Final Draft using Latec | 7:00 | 3 | 1:00 | 0.2 | All
2 | Solder the hardware (Pi's, temp and humid sensors) | 2:00 | 2 | 1:00 | 0.4 | Marcel
3 | Create CakePHP version of website | 8:00 | 5 | 3:30 | 0.4 | Justin
4 | Create c version of program to run spikes on server | 2:00 | 4 | 1:20 | 0.5 | All
5 | Start PHP unit tests | 20:00 | 5 | 0:00 | 0 | Justin
6 | RaspPI python/ajax code to report to web server | 2:00 | 2 | 0:00 | 0 | Justin
7 | Test DHT11 unit with RaspberryPi | 4:00 | 5 | 4:00 | 1 | Justin
8 | Configure Raspberry Pi xml hosting | 2:00 | 2 | 0:00 | 0 | Justin
9 | Configure laravel with new computer | 5:00 | 10 | 0:00 | 0
10 | Make Important Design Decisions | 1:00 | 10 | 0:00 | 0 | All