## Sheet1
Team 3.14, the RaspberryPi Temperature/Humidity Project
Marcel Englmaier, Jason Pearson, Mike Guzior, Justin Koehler
| Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
| Organize repo into correct subfolders | 1:00 | 10 | 1:00 | 1 | All
| Test DHT11 unit with RaspberryPi | 4:00 | 5 | 4:00 | 1 | Justin
| Solder the hardware (Pi's, temp and humid sensors) | 2:00 | 2 | 2:00 | 1 | Marcel
| Make Important Design Decisions | 1:00 | 10 | 1:00 | 1 | All
# | Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
1 | Feasability Report-Final Draft using Latex | 7:00 | 3 | 1:00 | 0.2 | All
3 | Create CakePHP version of website | 8:00 | 5 | 3:30 | 0.4 | Justin
4 | Create c version of program to run spikes on server | 2:00 | 4 | 1:20 | 0.5 | All
5 | Start PHP unit tests | 20:00 | 5 | 0:00 | 0 | Justin
6 | Configure Apache/NginX on RaspPi Decide on service | 2:00 | 7 | 0:30 | 0.25 | Jason
7 | Configure Wireless internet Access | 2:00 | 5 | 0:30 | 0.25 | Jason
8 | Configure Raspberry Pi xml hosting | 2:00 | 2 | 0:00 | 0 | Justin
9 | Configure laravel with new computer | 5:00 | 10 | 0:00 | 0 | Justin