## Sheet1
Team 3.14: Temperature Sensing Team
Marcel Englmaier, Justing Koehler, Jason Pearson
| Set Date: |  | End Date:
Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
Create General Information Description | 1 hour | 5 | 1 hour | 75% | All
This Weeks Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
Installation Documentation | 6 Hours | 10 | 2 Hours | 33.33% | All
Add Humidity modification | 10 Hours | 10 | 0 Hours | 0% | All