## Sheet1
Stories
# | Description | Estimated Time | Risk 1-10 | % Complete | Who | Date Completed
1 | Research Chipset to use | 1:00 | 2 | 100 | Marcel
2 | Research Temperature Sensor | 1:00 | 2 | 100 | Marcel
3 | Research Humidity Sensor | 1:00 | 2 | 100 | Marcel
4 | Acquire Specs from Client(Dr. Kapenga) | 1:00 | 10 | 0 | All
5 | Set up Git repo | 0 | 1 | 100 | Marcel
6 | Start looking into Laravell | 2:00 | 2 | 22 | All
7 | Meet with Previous project maker | 2:00 | 1 | 0 | All
8 | Test existing sensors for usability
9
10
11
12
13
14
15