## Sheet1
# | Tasks | Time | Risk 1-10 | % Complete
1 | Research Chipset to use | 1.0Hrs | 2 | 100
2 | Research Temperature Sensor | 1.0Hrs | 2 | 100
3 | Research Humidity Sensor | 1.0Hrs | 2 | 100
4 | Acquire Specs from Client(Dr. Kapenga) | 1.0Hrs | 10 | 100
5 | Set up Git repo | 0.05Hrs | 1 | 100
6 | Start looking into Laravell | 2.0Hrs | 2 | 22
7 | Contact Andrew for his code | 0.05Hrs | 1 | 100
8 | Meet with Andrew to discuss project | 1.0Hrs | 3 | 0