## Sheet1
Team 3.14, the RaspberryPi Temperature/Humidity Project
Marcel Englmaier, Jason Pearson, Mike Guzior, Justin Koehler
| Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
| Research Chipset to use | 1:00 | 2 | 1:00 | 100 | Marcel
| Research Temperature Sensor | 1:00 | 2 | 5:00 | 100 | Marcel
| Research Humidity Sensor | 1:00 | 2 | 1:25 | 100 | Marcel
| Acquire Specs from Client(Dr. Kapenga) | 1:00 | 10 | 1:00 | 100 | All
| Set up Git repo | 5:00 | 1 | 1:00 | 100 | Marcel
| Aquire old source code from Andrew | 2:00 | 6 | 2:00 | 100 | All
# | Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
1 | Feasability Report | 7:00 | 3 | 2:00 | 0.25 | All
2 | Solder the hardware (Pi's, temp and humid sensors) | 2:00 | 2 |  | 0 | All
3 | Install and configure Raspbian | 2:00 | 3 |  | 0 | All
4 | Install Laravel web server onto CS machines | 3:00 | 5 |  | 0 | Justin