## Sheet1
# | Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
1 | Research Chipset to use | 1:00 | 2 | 1:00 | Marcel
2 | Research Temperature Sensor | 1:00 | 2 | 5:00 | Marcel
3 | Research Humidity Sensor | 1:00 | 2 | 1:25 | Marcel
4 | Acquire Specs from Client(Dr. Kapenga) | 1:00 | 10 | 0 | All
5 | Set up Git repo | 0 | 1 | 1:00 | Marcel
6 | Start looking into Laravell | 2:00 | 2 | 2:30 | All
7
8
9