## Sheet1
Team 3.14: Temperature Sensing Team
Marcel Englmaier, Justing Koehler, Jason Pearson
Oct 26 - Nov 1
Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
This Weeks Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
Installation Documentation | 6 Hours | 4 | 10 Hours | 90% | All
Add Humidity modification | 10 Hours | 6 | 8 Hours | 30% | All
Create Ruby Version of Site | 45 Hours | 10 | 25 Hours | 50% | All
Revamp Presentation | 20 Hours | 7 | 12 Hours | 90% | All