## Sheet1
# | Tasks | Risk | Time Estimate | Time Actual | % Complete | User | Code Review
1 | Acquire Specs from Client(Dr. Kapenga) | 10 | 1.0Hrs | 1.0Hrs | 100 | All | X
2 | Start looking into Laravell | 2 | 2.0Hrs | 0Hrs | 22 | All | X
3 | Contact Andrew for his code | 1 | 0.05Hrs | 0.05Hrs | 100 | Jason | X
4 | Meet with Andrew to discuss project | 3 | 1.0Hrs | 0Hrs | 0 | All | X