## Sheet1
Team 3.14: Temperature Sensing Team
Marcel Englmaier, Justing Koehler, Jason Pearson
| Set Date: |  | End Date:
Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
Create General Information Description | 1 hour | 5 | 3 hour | 100% | All
This Weeks Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
Installation Documentation | 6 Hours | 4 | 7 Hours | 60% | All
Add Humidity modification | 10 Hours | 6 | 3 Hours | 10% | All
Create Ruby Version of Site | 45 Hours | 10 | 12 Hours | 15% | All