## Sheet1
Team 3.14: Temperature Sensing Team
Marcel Englmaier, Justing Koehler, Jason Pearson
| Set Date: |  | End Date:
Completed Tasks | Time Estimate | Risk | Time Actual | % Complete | Code Review
Reconfigure Laravel for CS Servers | 3:00 | 10 | 7:00 | 100%
Ruby on Rails Spike | 3:00 | 2 | 3:00 | 100%
This Weeks Tasks | Time Estimate | Risk | Time Actual | % Complete | Teammate
Adding Humidity to site | 5:00 | 10 | 2:30 | 67%
Creation of better wiring | 2:00 | 5 | 2:00 | 54%
Project Document | 15:00 | 10 | 3:00 | 20%
Presentation | 10:00 | 10 | 2:00 | 33%
User Manuals | 15:00 | 10 | 4:00 | 15%